## Dashboard
CapEx Investment Monitoring Tool
Total CapEx Budget (PLN) | 10885000
Total Actual Spend (PLN) | 11243000
Total Variance (PLN) | 358000
Budget Utilization % | 103.3%
Projects Flagged | 7
High Risk Projects | 3
Projects On Track | 18
Active Plant Locations | 4
Total Projects | 25
Go to CapEx Tracker
Go to Fixed Assets

## CapEx Tracker
Project ID | Project Name | Category | Plant Location | Project Manager | Planned Budget (PLN) | Actual Spend (PLN) | Variance (PLN) | Variance (%) | Completion (%) | Status Flag | Execution Risk
INV-001 | Production Line Modernization | Machinery | Plant A | PM-101 | 500000 | 547000 | 47000 | 9.4% | 85% | OK | ON TRACK
INV-002 | Warehouse Expansion | Construction | Plant A | PM-102 | 1200000 | 1190000 | -10000 | -0.8333% | 90% | OK | ON TRACK
INV-003 | Packaging Equipment Upgrade | Machinery | Plant B | PM-103 | 320000 | 290000 | -30000 | -9.375% | 100% | OK | ON TRACK
INV-004 | ERP System Migration | Technology | HQ | PM-104 | 180000 | 205000 | 25000 | 13.89% | 60% | FLAG | REVIEW
INV-005 | Production Hall Renovation | Construction | Plant A | PM-101 | 430000 | 431000 | 1000 | 0.2326% | 45% | OK | ON TRACK
INV-006 | Forklift Fleet Renewal | Equipment | Plant A | PM-105 | 95000 | 88000 | -7000 | -7.368% | 100% | OK | ON TRACK
INV-007 | Laboratory Equipment | Machinery | Plant C | PM-106 | 210000 | 267000 | 57000 | 27.14% | 70% | FLAG | REVIEW
INV-008 | Cooling System Overhaul | Machinery | Plant B | PM-103 | 375000 | 380000 | 5000 | 1.333% | 95% | OK | ON TRACK
INV-009 | Solar Panel Installation | Construction | Plant A | PM-102 | 890000 | 820000 | -70000 | -7.865% | 75% | OK | ON TRACK
INV-010 | Business Intelligence Platform | Technology | HQ | PM-104 | 460000 | 512000 | 52000 | 11.3% | 55% | FLAG | REVIEW
INV-011 | Conveyor System Replacement | Machinery | Plant A | PM-101 | 145000 | 143000 | -2000 | -1.379% | 100% | OK | ON TRACK
INV-012 | Office Refurbishment | Construction | HQ | PM-105 | 210000 | 275000 | 65000 | 30.95% | 35% | FLAG | HIGH RISK
INV-013 | Fire Safety System | Equipment | Plant B | PM-103 | 88000 | 91000 | 3000 | 3.409% | 100% | OK | ON TRACK
INV-014 | Automated Palletizer | Machinery | Plant A | PM-102 | 670000 | 695000 | 25000 | 3.731% | 80% | OK | ON TRACK
INV-015 | Company Vehicle Fleet | Vehicles | Plant A | PM-105 | 310000 | 298000 | -12000 | -3.871% | 100% | OK | ON TRACK
INV-016 | Quality Control Lab | Technology | Plant C | PM-106 | 540000 | 610000 | 70000 | 12.96% | 45% | FLAG | HIGH RISK
INV-017 | Boiler Room Upgrade | Machinery | Plant B | PM-103 | 290000 | 287000 | -3000 | -1.034% | 100% | OK | ON TRACK
INV-018 | Wastewater Treatment Plant | Construction | Plant A | PM-101 | 175000 | 174000 | -1000 | -0.5714% | 98% | OK | ON TRACK
INV-019 | Security Camera Network | Technology | Plant A | PM-105 | 62000 | 68000 | 6000 | 9.677% | 90% | OK | ON TRACK
INV-020 | Specialized Production Unit | Equipment | Plant C | PM-106 | 420000 | 463000 | 43000 | 10.24% | 50% | FLAG | REVIEW
INV-021 | Compressed Air System | Machinery | Plant B | PM-103 | 195000 | 193000 | -2000 | -1.026% | 100% | OK | ON TRACK
INV-022 | Staff Facilities Renovation | Construction | Plant A | PM-105 | 130000 | 128000 | -2000 | -1.538% | 100% | OK | ON TRACK
INV-023 | Pilot Production Plant | Construction | Plant C | PM-106 | 980000 | 1150000 | 170000 | 17.35% | 30% | FLAG | HIGH RISK
INV-024 | Robotics Integration Project | Technology | Plant A | PM-102 | 1450000 | 1380000 | -70000 | -4.828% | 65% | OK | ON TRACK
INV-025 | Loading Dock Expansion | Construction | Plant A | PM-101 | 560000 | 558000 | -2000 | -0.3571% | 99% | OK | ON TRACK

## Fixed Assets
Asset ID | Asset Name | Category | Purchase Date | Original Value (PLN) | Book Value (PLN) | Location | Status | SAP Asset No. | Asset Review Flag
FA-001 | Production Line A | Machinery | 4389100% | 850000 | 425000 | Plant A | Active | SAP-10045
FA-002 | Forklift Unit #3 | Vehicles | 4436200% | 95000 | 15833.3333 | Plant A | Active | SAP-10078
FA-003 | Server Room Infrastructure | Technology | 4377900% | 180000 | 0 | HQ | Active | SAP-10031 | ⚑ REVIEW NEEDED
FA-004 | Decommissioned Production Unit | Machinery | 4202600% | 320000 | 0 | Plant B | Disposed | SAP-10012
FA-005 | Industrial Cooling Unit | Machinery | 4465600% | 210000 | 140000 | Plant A | Active | SAP-10091
FA-006 | Company Vehicle Fleet | Vehicles | 4406100% | 310000 | 0 | Plant A | Active | SAP-10055 | ⚑ REVIEW NEEDED
FA-007 | Laboratory Instrument Set | Technology | 4497100% | 75000 | 18750 | Plant C | Active | SAP-10103
FA-008 | Warehouse Shelving System | Equipment | 4331100% | 45000 | 0 | Plant A | Under Maintenance | SAP-10022 | ⚑ REVIEW NEEDED
FA-009 | Heavy Machinery Unit | Machinery | 4445900% | 1200000 | 700000 | Plant C | Active | SAP-10110
FA-010 | Quality Testing Equipment | Technology | 4539300% | 320000 | 160000 | Plant B | Active | SAP-10125
Formulas:
Book Value (PLN) = IF([Status]="Disposed",0,MAX(0,[Original Value (PLN)]-(([Original Value (PLN)]/IFS([Category]="Machinery",12,[Category]="Construction",30,[Category]="Technology",4,[Category]="Vehicles",6,[Category]="Equipment",8,[Category]="Furniture",7,TRUE,10))*(YEAR(TODAY())-YEAR([Purchase Date])))))